## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP)
State: | LAGOS
Reporting period: | FY 2023
SABER Focal Person: | Mrs. Solape Hammond
List of contributing entities: | Office of Sustainable Development Goals & Investments;Office of Transformation, Creativity and Innovation (OTCI); Lagos Internal Revenue Service; Ministry of Finance, Ministry of Economic Planning and Budget; Office of Transformation, Creativity and Innovation; Ministry of Commerce and Industry; Ministry of Agriculture and Cooperatives; Ministry of Science and Technology, Lagos State Waste Management Agency, Lagos State Water Corporation, Lagos State Motor Vehicle Adminstration Agency
URL Link to the published BERAP |  | Lagos MEPB ¦
Is this plan approved by the State Executive Council (SEC) |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  | 2023-01-30

## BERAP
LAGOS STATE BUSINESS-ENABLING REFORM ACTION PLAN (2023)
Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Estimated Cost | Planned Start Date | Planned End Date
Improve efficiency in property registration and land-based investment process | Launch automated Lagos State e-GIS with functions for: | Complete User Acceptance Test and sign off on customer portal | Launch customer property registration portal | Citizens and businesses in Lagos | Lagos State Lands Bureau | Ministry of Finance | To be determined | Q1, 2023 | Q3,2023
| -Search | Ensure Full Production infrastructure in place | Complete process automation/elimination of manual processing and filing for land titles | Existing and prospective Land owners/acquirers |  | Ministry of Science and Technology
| -Allocation of State Land | Setup Production Environment for enhancements | Full automation of assessment of applicable fees | Lagos State Government |  | Office of Transformation, Creativity and Innovation (OTCI)
| -Governor’s Consent | Test entire system - Database /Application /Server Backups / Disaster Recovery | Automation of payment of fees for land registration with system generated invoice
Define clear process for Cutover and RollBack
Establish customer support mechanisms
Complete internal / external stakeholder engagement
Optimise efficiency of Government-to-Business (G2B) processes to improve Lagos State's competitiveness and attractiveness as a target investment location | Consolidate G2B channel/front end to deliver seamless experience and engagement for investors and businesses for services, registration, licenses, approvals, enquiries and payments across Lagos State Ministries, Departments and Agencies | Catalogue G2B services, registration, licensing, approvals, enquiries and payments across Lagos MDAs | Improved ease of access to and quality of G2B services and better investor engagement enabled by multi-channel(physical location and digital) One Stop Center | Prospective and existing Investors | Office of Sustainable Development Goals and Investments | Lagos Internal Revenue Service | To be determined ' | Q1, 2023 | Q2, 2024
|  | Identify top/highest priority G2B services, registration, licensing, approvals, enquiries and payments across Lagos MDAs for investors and businesses | - Deliver 1 physical location hosting services desks of multiple MDAs processing up to 200 investor/business transactions/ service fulfillment | Businesses in Lagos State |  | Lagos State Water Corporation
|  | Define target operating model for Lagos State lnvestor Experience Center (One-Stop-Center) locations and for G2B front-end/interface | - Digital platorm to provide (1) informational requirements for investing businesses (2) highest priority/instances of G2B services -- at least 1 high demand/traffic G2B service, registration, license, approval, enquiry and/or payment process across 5 identiied Lagos State Ministries, Departments and Agencies |  |  | Lagos State Motor Vehicle Administration Agency
|  | Liaise with Relevant MDA's to understand hosted desk arrangements |  |  |  | Lagos State Signage and Advertisement Agency
|  | Define specific functions of institutions and agencies to be hosted at the lnvestor experience (One-Stop-Center) locations | Up to 25% reduction in transaction fulfilment/ service turnaround time |  |  | Ministry of Science and Technology
|  | Define the processes and channels for integration with the fulfilling/approving MDAs for hosted desks |  |  |  | Lands Bureau
|  | Define RACI model (governance structure and roles / responsibilities that will be assigned to relevant parties using the RACI Model) and governance framework |  |  |  | Nigeria Immigration Service
|  | Define and agree SLAs with MDAS for in scope G2B services, registration, licensing, approvals and enquiries |  |  |  | Federal Inland Revenue Sservice (FIRS)
|  | Design One Stop Center model - hosted desks, physical layout and floor plan, processes, governance, technology, etc |  |  |  | Office of Transformation, Creativity and Innovation (OTCI)
|  | Identify physical locations for Investor Experience (One Stop Center) for G2B services, approvals and interface with investors and businesses |  |  |  | Ministry of Finance
|  | Design and build pilot physical Investor Experience (One Stop Center) location - building, infrastructure, furnishing, networks and communications etc |  |  |  | Ministry of Economic Planning and Budget
Launch Investor Experience (One Stop Center) location with hosted desks for MDAS processing requirements of investors and businesses
Define target operating model for digital (One stop shop) platform for G2B services
Design interface and handoffs for seamless integration with service fulfiment processes of MDAs
Design and build digital platform/single G2B frontend
Pilot digital G2B Channel/ Frontend with highest priority services/processing requirements of investors and businesses
| Data Asset of primary and secondary data of Investors and Businesses in Lagos State as single source of information for G2B service fulfilment and basis for Government analysis, insight and policies | Determine primary and secondary data requirements of MDAs about investors and businesses for efficency of G2B service fulfilment and ''single version of truth'' in Lagos State | Launch Lagos State Investors and Business Database and enroll up to 2,000 entities with existing businesses and 50 interests/ potential investors | Lagos State Government Executives and MDAs | Office of Sustainable Development Goals and Investments | Lagos Internal Revenue Service | To be determined | Q3, 2023 | Q1, 2024
|  | Define comprehensive data architecture and strategy for capturing existing data/information across MDAs | Establish unique identifier for tracebility and achieve 60% completion of primary and secondary data for enrolled businesses and investors |  | Lagos State Bureau of Statistics | Ministry of Commerce and Industry
|  | Determine appropriate digital identifier for investors and businesses to be used across all Lagos State MDAs | Profile Lagos State programs and Investments opportunities across sectors |  |  | Ministry of Finance
|  | Integrate data cleaning and data collection into service processes | Improved data for understanding and analysing trends and investor/business actions and inflow of investments into economic sectors |  |  | Ministry of Economic Planning and Budget
|  | Pilot data aggregation |  |  |  | Office of Transformation, Creativity and Innovation (OTCI)
| Tiered Key Account/Relationship management and service model for investors and business operators to increase engagement and responsiveness of services | Refine Account Management Tiering model and define classification and tiering criteria for Strategic, Impact and Growth Investors and Businesses | Set up account/relationship responsibility for 50 highest priority strategic investors and businesses to prioritise service management and engagement and support Service Level management | Strategic and highest priority investors and businesses | Office of Sustainable Development Goals and Investment | Office of Transformation, Creativity and Innovation (OTCI) | To be determined | Q1, 2023 | Q4,2023
|  | Define target service and engagement model to optimise service and engagement for investors and businesses |  |  |  | Ministry of Science and Technology
|  | Implement Investor Relationship Management technology | Track, report and monitor service fulfilment against service targets and case management to ensure 80% SLA performance on G2B service requests and transactions
Define and implement organisation model to deliver tiered account management model - Relationship Teams for Strategic Investor/Businesses; On-Call Service Teams for Impact Investors/Businesses; Assisted Digital Channel for Growth Investors/Businesses and Self Service Ditial Channels for Other Investors/Businesses
| Simplify / harmonise process for accessing government services | Catalogue registration procedures, approvals, licensing and levies/government payments for business entity types by sector across Lagos State MDAs | Finalise and publish reference document/FAQs of registration and regulatory process approvals, licensing and levies/government payments for 4 prioirity economic sectors across 5 highest impact/service fulfiment MDAs | Prospective and existing Investors | Office of Transformation, Creativity and Innovation (OTCI) | Ministry of Science and Technology | To be determined | Q1,2023 | Q4, 2023
|  | Automate consolidated compliance checklist of approvals, licensing and levies/government payments status across Lagos State MDAs |  | Businesses in Lagos State |  | Office of Sustainable Development Goals and Investment
Integrate compliance status checklist into G2B service processes
Deployment of QR Code for in scope services and supports.
Transform and improve performance on Lagos Investment Promotion Agency across investor process lifecycle | Improve environment for global competitiveness and promote inward and outward Foreign Direct Investment in Lagos State. investment Promotion Agency Processes and Capability areas include: Information Provision, Marketing and Promotion, Advisory Services, Facilitation Services, Processing Services, Approvals, Investor Aftercare | Prioritise Investment promotion processes based on impact on investors and businesses | Improve 2 high impact Promotion Agency process from interest/exploration, initial enquiry, deal origination to completion. | Prospective and existing Investors | Office of Sustainable Development Goals and Investments | Ministry of Commerce and Industry | To be determined | Q1, 2023 | Q4, 2023 | "Under ""description and Key Targets"", it currently only describes target beneficiaries; please add Clear description of target objective to be achieved by the action. Example: Improved investor support process from deal origination to completion. Please, enter planned start and end date by action step
|  | Identify highest priority process and services |  | Businesses in Lagos State |  | Ministry of Agriculture and Cooperatives,
|  | Map and analyze existing process |  |  |  | Lagos State Inland Revenue Service,
|  | Identify process, capability and talent gaps |  |  |  | Ministry of Science and Technology Information Communication,
|  | Define target end state operating model, processes, capabilities, organisation and capabilities |  |  |  | Ministry Of Energy And Mineral Resources,
|  | Define road map to deliver target end state |  |  |  | Ministry of Physical Planning and Urban Development,
| Increase inflow of Diaspora Investments into Lagos State | Create Diaspora investment desk in OSDGI as a focal point for the coordination of investments, programmes, and activities between the diaspora community and Lagos state |  |  |  | Lands Bureau
|  | Assist Diaspora investors to process business set up with strategic partnerships with the Corporate affairs commissions and other key processing parties in the government. |  |  |  | Nigeria Immigration Service
|  | Influence Investment perception and Ease of doing business about Lagos State |  |  |  | Federal Inland Revenue Sservice (FIRS)
|  | Introduce follow-up initiatives to retain investments, encourage & expedite reinvestment, and anchoring investors |  |  |  | Office of Transformation, Creativity and Innovation (OTCI)
| Transparent, evidence based monitoring and reporting of progress on Business Enabling Reform | Document Reform Program initiatives, responsibilities, milestones and expected deliverables across MDAs and obtain sign off. | Evidence based, transparent tracking, monitoring and reporting of status and progress on Business Enabling Reforms across MDAs | Lagos State Government and MDAs | Office of Transformation, Creativity and Innovation (OTCI) | Lagos Inland Revenue Service | To be determined | Q1, 2023 | Q4,2023
|  | Design and build web based portal for tracking, monitoring and reporting on Lagos State business enabling reforms | Launch web based portal and publish Business Enabling Reform Program status | Investors and Business Stakeholders | Office of Sustainable Development Goals and Investments | Office of Public, Private Partnership
|  | Design Portal architecture - web front end and data source/input by MDA's program managers |  | Lagos State Public and Citizens |  | Ministry of Economic Planning and Budget
|  | Build and test web based portal and business anabling reform data input forms and templates |  | Development Partners and Agencies |  | Lagos State Motor Vehicle Administration Agency
|  | Implement and commence tracking, monitoring and reporting status of and progress on Business Enabling Reforms |  |  |  | Lands Bureau
|  | Maintain and update web based Portal |  |  |  | Ministry of Finance
Lagos State Signage and Advertisement Agency
Ministry of Science and Technology
Lagos State Water Corporation
Ministry of Commerce, Industry and Cooperatives
Ministry of Agriculture
Ministry of Finance
Improve Transparency of official fees, levies and payments and service standards | Transparency of Official Fees & Procedures of G2B services provided by 5 critical MDAs | For the 5 MDAs with the highest investor/business operator transaction traffic, iIdentify 3 additional priority services | Publish online transparent, up to date, accurate data on official fees, levies, payments and procedures for 3 priority services across 5 highest impact/service fulfiment MDAs |  | Office of Transformation, Creativity and Innovation. | Ministry of Economic Planning and Budget | To be determined | Q1, 2023 | Q3, 2024
|  | Document fees, procedures and service delivery timelines. |  |  |  | Lagos Internal Revenue Service
|  | Publish information on online - MDA website, G2B digital platform. |  |  |  | Lagos State Water Corporation
|  | Create 'Frequently Asked Questions' on respective MDA website and G2B digital platform. |  |  |  | Lagos State Motor Vehicle Admistration Agency
| Deepen Civic Engagement by making Operational Procedures and Related Services/Fees/Charges for G2C services and functions more accessible in a timely/simplified and easy to understand format. | Document scope and coverage of G2C services and interactions and determine operational procedures and related services/fees/charges across Lagos State Government MDAs | Deepen citizens' participation and improve transparency of procedures, fees, charges and service promise for Government services and functions. | Lagos State Public and Citizens | Office of Civic Engagement | Ministry of Science and Technology | To be determined | Q1, 2023 | Q4, 2023
|  | Design digital G2C engagement and service management frontend across Lagos Government MDAs | Direct G2C channel for citizens' feedback; engagement; service monitoring across 5 high impact Government MDAS. | Lagos State Government and MDA executives | Office of Transformation, Creativity and Innovation. | Office of Sustainable Development Goals and Investments,
|  | Build and develop proof of concept to validate Citizen's Gate design | Availability of 1 free Toll Line (767) for non-security and non-emergency issues integrated to service portal and case management for service delivery issues for the 5 critical MDAs |  |  | Lagos State Motor Vehicle Admistration Agency
|  | Define and agree release plan for Citizens' Gate functionalities | Monitor, track and produce weekly reports of case management and service responsiveness and performance across MDAS |  |  | Lagos State Waste Management Authority
|  | Design, develop, pilot and implement Citizen's Gate functionalities in line with release plan: |  |  |  | Lagos Internal Revenue Service
Extend coverage of Lagos State contact center and toll free lines(112,767 etc) to include non-emergency functions and service requests
Implement case management and resolution tracking to monitor, track and report service fulfilment and closure
Integrate Citizens' Gate frontend to the service portals of fulfilling MDAS
Develop Service Catalog and Service commitment on Citizens' Gate
Track, monitor and report Service performance across Lagos State Govt entities
Harmonisation of Fees and Levies for Interstate Trade | Promote Inter-Governmental Cooperation by Removing/Significantly Reducing Multiple Taxations | Establish baseline Database of Fees, Levies and payments by entities in each sector collected across Lagos State MDAS - prioritise business facing MDAs i.e. Ministry of Transport, Commerce, Industry and Cooperative etc. | Create single accurate version of truth for fees, levies andpayments by entities in each sector to Lagos State Government mapped to the approved levies by the Joint Tax Board . | Lagos State Businesses | Ministry of Finance | Office of Sustainable Development Goals and Investments | To be determined | Q1, 2023 | Q4, 2023/ Q1, 2024
|  | Map and Harmonise Fees, Levies and payment schedules for entity types across sectors across MDAs (i.e. identify duplications and overlaps) |  | Lagos State Public and Citizens | Lagos State Internal Revenue Service, | Ministry of Economic Planning and Budget
|  | Update the State's Revised Revenue Code. |  | Lagos State Government Revenue Agencies |  | Ministry of Transportation+I89
|  | Obtain Approval and map to schedule of approved sub-nationals fees, levies and payments by the Joint Tax Board |  |  |  | Ministry of Commerce, Industry and Cooperatives.
Ministry of Science and Technology.
[11 empty] | Office of Transformation, Creativity and Innovation | Ministry of Finance | Ministry of Economic Planning and Budget | OTCI | OTCI/LBS

## Progress Report (hidden)
STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
| The focus area for the reforms eg transparency of official fees and procedures | What the State intends to achieve by implementing the Business Enabling Reform | Very detailed, step by step process on how the objective will be achieved | User, beneficiaries, recipient of the reform Explain actions and/or sub-actions and include targets | One MDA responsible for the action/activity | Supporting MDAs | Estimated budget for the action/activity | When you commit to start the implementation of the actions | When you commit to complete the actions and achieve your targets | Indicate whether the action/activity is completed, ongoing - on time, ongoing - delayed or dropped | Describe the status of each action, explaining reasons for any delays or actions being dropped. Explain any changes that occurred during implementation affecting start and end dates | Describe next steps for the outstanding actions. For example, is the action getting carried over to the following year's action plan?
1 | Increase Transparency of the State's Tax Administration and procedures. | This reform will deepen Transparency in Tax Administration in Lagos State.. | Currently Reviewing Haulage Fees across all MDAs for ease of harmonisation. | The General Public | Lagos Internal Revenue Service | Ministry of Transportation | Amount (in Naira) | Day, Month, Year | Day, Month, Year
|  |  | Obtained Data from Relevant MDAs | Ministry of Transportation |  | Ministry of Physical Planning and Urban Development | TBD | Ongoing | TBD | Ongoing | Ongoing | TBD
|  |  | Sanitisation of Data obtained to increase the integrity of data base | Ministry of Physical Planning and Urban Development |  | Ministry of Energy | TBD | Ongoing | TBD | Ongoing | Ongoing | TBD
|  |  |  | Ministry of Energy…..amongst others |  | Ministry of Finance | TBD | Ongoing | TBD | Ongoing | Ongoing | TBD
[6 empty] | Ministry of Economic Planning and Budget | TBD | Ongoing | TBD | Ongoing | Ongoing | TBD
[6 empty] | Office of Transformation, Innovation and Creativity | TBD | Ongoing | TBD | Ongoing | Ongoing | TBD